## PMR
DepEd Caloocan - Tala Elementary School | [9 empty] | Procurement Monitoring Report as of July 2026
[5 empty] | Actual Procurement Activities | [13 empty] | ABC (PhP) |  |  | Contract Cost (PhP) |  |  |  | Date of Receipt of Invitation
Code (PAP) | Procurement Project | PMO/End-User | Is this an Early Procurement Activity? | Mode of Procurement | Pre-Proc Conference | Ads/Post of IB | Pre-bid Conf | Eligibility Check | Sub/Open of Bids | Bid Evaluation | Post Qual | Date of BAC Resolution Recommending Award | Notice of Award | Contract Signing | Notice to Proceed | Delivery/ Completion | Inspection & Acceptance | Source of Funds | Total | MOOE | CO | Total2 | MOOE2 | CO3 | List of Invited Observers | Pre-bid Conf4 | Eligibility Check5 | Sub/ Open of Bids6 | Bid Evaluation7 | Post Qual8 | Delivery/ Completion/ Acceptance (If applicable) | Remarks (Explaining changes from the APP)
COMPLETED PROCUREMENT ACTIVITIES | [21 empty] | 0
| Printing of Third Periodical Test | TALA ELEMENTARY SCHOOL | No | Sec. 34 - Small-Value Procurement | 2026-02-02 | 2026-02-02 | 2026-02-02 | 2026-02-02 | 2026-02-09 | 2026-02-09 | 2026-02-09 | 2026-02-09 | 2026-02-09 | 2026-02-11 | 2026-02-09 | 2026-02-13 | 2026-02-13 | MOOE | 99999.25 | 99999.25 |  | 97930.3 | 97930.3 |  |  | 2026-02-02 | 2026-02-02 | 2026-02-09 | 2026-02-09 | 2026-02-09 | 2026-02-13 | Completed
| Printing of Fourth Periodical Test | TALA ELEMENTARY SCHOOL | No | Sec. 34 - Small-Value Procurement | 2026-03-11 | 2026-03-11 | 2026-03-11 | 2026-03-11 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-18 | 2026-03-18 | 2026-03-18 | 2026-03-18 | 2026-03-23 | 2026-03-23 | MOOE | 99999.25 | 99999.25 |  | 98619.95 | 98619.95 |  |  | 2026-03-11 | 2026-03-11 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-23 | Completed
| Purchase of Graduation, Moving UP, PRAISE 2026 | TALA ELEMENTARY SCHOOL | No | Sec. 34 - Small-Value Procurement | 2026-03-06 | 2026-03-06 | 2026-03-06 | 2026-03-06 | 2026-03-12 | 2026-03-12 | 2026-03-12 | 2026-03-16 | 2026-03-13 | 2026-03-17 | 2026-03-16 | 2026-03-23 | 2026-03-23 | MOOE | 249965 | 249965 |  | 249875 | 249875 |  |  | 2026-03-06 | 2026-03-06 | 2026-03-12 | 2026-03-12 | 2026-03-12 | 2026-03-23 | Completed
| Purchase of Office Supplies | TALA ELEMENTARY SCHOOL | No | Sec. 34 - Small-Value Procurement | 2026-03-11 | 2026-03-11 | 2026-03-11 | 2026-03-11 | 2026-03-13 | 2026-03-13 | 2026-03-13 | 2026-03-18 | 2026-03-17 | 2026-03-18 | 2026-03-18 | 2026-03-23 | 2026-03-23 | MOOE | 46996.36 | 46996.36 |  | 46996.36 | 46996.36 |  |  | 2026-03-11 | 2026-03-11 | 2026-03-13 | 2026-03-13 | 2026-03-13 | 2026-03-23 | Completed
| Procurement of Rehabilitation of Water Connection | TALA ELEMENTARY SCHOOL | No | Sec. 34 - Small-Value Procurement | 2026-04-01 | 2026-04-01 | 2026-04-01 | 2026-04-01 | 2026-04-08 | 2026-04-08 | 2026-04-08 | 2026-04-13 | 2026-04-13 | 2026-04-15 | 2026-04-15 | 2026-04-29 | 2026-04-29 | MOOE | 240000 | 240000 |  | 237530.46 | 237530.46 |  |  | 2026-04-01 | 2026-04-01 | 2026-04-08 | 2026-04-08 | 2026-04-08 | 2026-04-29 | Completed
| Procurement of Repair and Declogging of All Comfort Rooms | TALA ELEMENTARY SCHOOL | No | Sec. 34 - Small-Value Procurement | 2026-05-08 | 2026-05-08 | 2026-05-08 | 2026-05-08 | 2026-05-13 | 2026-05-13 | 2026-05-13 | 2026-05-14 | 2026-05-14 | 2026-05-18 | 2026-05-18 | 2026-05-29 | 2026-05-29 | MOOE | 240000 | 240000 |  | 234841.82 | 234841.82 |  |  | 2026-05-08 | 2026-05-08 | 2026-05-13 | 2026-05-13 | 2026-05-13 | 2026-05-29 | Completed
| Gender and Development | TALA ELEMENTARY SCHOOL | No | Sec. 34 - Small-Value Procurement | 2026-05-11 | 2026-05-11 | 2026-05-11 | 2026-05-11 | 2026-05-13 | 2026-05-13 | 2026-05-13 | 2026-05-14 | 2026-05-14 | 2026-05-21 | 2026-05-21 | 2026-05-29 | 2026-05-29 | MOOE | 203600 | 203600 |  | 202950 | 202950 |  |  | 2026-05-11 | 2026-05-11 | 2026-05-13 | 2026-05-13 | 2026-05-13 | 2026-05-29 | Completed
| Procurement of Rehabilitation of Ancillary Rooms (LIBRARY/LRMDS) | TALA ELEMENTARY SCHOOL | No | Sec. 34 - Small-Value Procurement | 2026-05-11 | 2026-05-11 | 2026-05-11 | 2026-05-11 | 2026-05-13 | 2026-05-13 | 2026-05-13 | 2026-05-14 | 2026-05-14 | 2026-05-18 | 2026-05-18 | 2026-05-29 | 2026-05-29 | MOOE | 200000 | 200000 |  | 195622.06 | 195622.06 |  |  | 2026-05-11 | 2026-05-11 | 2026-05-13 | 2026-05-13 | 2026-05-13 | 2026-05-29 | Completed
| Purchase of Office Equipment | TALA ELEMENTARY SCHOOL | No | Sec. 34 - Small-Value Procurement | 2026-05-12 | 2026-05-12 | 2026-05-12 | 2026-05-12 | 2026-05-15 | 2026-05-15 | 2026-05-15 | 2026-05-18 | 2026-05-18 | 2026-05-20 | 2026-05-19 | 2026-05-29 | 2026-05-29 | MOOE | 47000 | 47000 |  | 47000 | 47000 |  |  | 2026-05-12 | 2026-05-12 | 2026-05-15 | 2026-05-15 | 2026-05-15 | 2026-05-29 | Completed
| Printing of Diagnostic Test SY 2026-2027 | TALA ELEMENTARY SCHOOL | No | Sec. 34 - Small-Value Procurement | 2026-06-08 | 2026-06-08 | 2026-06-08 | 2026-06-08 | 2026-06-10 | 2026-06-10 | 2026-06-10 | 2026-06-11 | 2026-06-11 | 2026-06-15 | 2026-06-15 | 2026-06-18 | 2026-06-18 | MOOE | 99998.79 | 99998.79 |  | 99317.75 | 99317.75 |  |  | 2026-06-08 | 2026-06-08 | 2026-06-10 | 2026-06-10 | 2026-06-10 | 2026-06-18 | Completed
| Purchase of Office Supplies | TALA ELEMENTARY SCHOOL | No | Sec. 34 - Small-Value Procurement | 2026-06-08 | 2026-06-08 | 2026-06-08 | 2026-06-08 | 2026-06-10 | 2026-06-10 | 2026-06-10 | 2026-06-11 | 2026-06-11 | 2026-06-15 | 2026-06-15 | 2026-06-18 | 2026-06-18 | MOOE | 84160 | 84160 |  | 83935 | 83935 |  |  | 2026-06-08 | 2026-06-08 | 2026-06-10 | 2026-06-10 | 2026-06-10 | 2026-06-18 | Completed
| WINS Supplies & Materials | TALA ELEMENTARY SCHOOL | No | Sec. 34 - Small-Value Procurement | 2026-06-08 | 2026-06-08 | 2026-06-08 | 2026-06-08 | 2026-06-10 | 2026-06-10 | 2026-06-10 | 2026-06-11 | 2026-06-11 | 2026-06-15 | 2026-06-15 | 2026-06-18 | 2026-06-18 | MOOE | 49996 | 49996 |  | 49996 | 49996 |  |  | 2026-06-08 | 2026-06-08 | 2026-06-10 | 2026-06-10 | 2026-06-10 | 2026-06-18 | Completed
[19 empty] | 0 |  |  | 0
[19 empty] | 0 |  |  | 0
[19 empty] | 0 |  |  | 0
[19 empty] | 0 |  |  | 0
[5 empty] | 2026-04-01 | [13 empty] | 0 |  |  | 0
[18 empty] | Total Allotted Budget of Procurement Activities | 1661714.65 | 1661714.65 | 0
[18 empty] | Total Contract Price of Procurement Activities Conducted |  |  |  | 1644614.7 | 1644614.7 | 0
[18 empty] | Total Savings (Total Allotted Budget - Total Contract Price) | 17099.95
Code (PAP) | Procurement Project | PMO/End-User | Is this an Early Procurement Activity? | Mode of Procurement | Pre-Proc Conference | Ads/Post of IB | Pre-bid Conf | Eligibility Check | Sub/Open of Bids | Bid Evaluation | Post Qual | Date of BAC Resolution Recommending Award | Notice of Award | Contract Signing | Notice to Proceed | Delivery/ Completion | Inspection & Acceptance | Source of Funds | Total | MOOE | CO | Total2 | MOOE2 | CO3 | List of Invited Observers | Pre-bid Conf4 | Eligibility Check5 | Sub/Open of Bids6 | Bid Evaluation7 | Post Qual8 | Delivery/ Completion/ Acceptance (If applicable) | Remarks (Explaining changes from the APP)
ONGOING PROCUREMENT ACTIVITIES
[18 empty] | Total Allotted Budget of On-going Procurement Activities | 0 | 0 | 0 | 0 | 0 | 0
|  | Prepared by: | [7 empty] | Recommended for Approval by: | [11 empty] | APPROVED:
|  | MITZEL D. BARRIENTOS | [7 empty] | RODA T. CANALES | [11 empty] | REMEDIOS B. LICONG
|  | BAC Secretariat | [7 empty] | BAC Chairperson | [11 empty] | Head of the Procuring Entity

## Validation Menu (hidden)
REMARKS | STATUS | STAGE OF PROCUREMENT | Source of Funds | Mode of Procurement
Awarded with issued Notice of Award | Awarded | Invitation To Bid | Government of the Philippines (current year's budget) | Competitive Bidding
Completed | Completed | Pre-bidding Conference | Government of the Philippines (continuing budget) | Limited Source Bidding
Ongoing Procurement Process | Failed | Opening of Bids | Government of the Philippines (current year's and continuing budget) | Direct Contracting
Failed under Section 32.2.1 (a) | Ongoing | Bid Evaluation | Grant by an International Financing Institution | Repeat Order
Failed under Section 35.1 (a) |  | Post-Qualification | Loan from an International Financing Institution | Shopping 52.1(a) - Unforeseen Contingency
Failed under Section 35.1 (b) |  | BAC Resolution |  | Shopping 52.1(b) - Regular Office Supplies and Equipment not available in PS
Failed under Section 35.1 (c) |  | Award |  | Negotiated Procurement - Two Failed Biddings
Failed under Section 41 (b) |  | Cancelled |  | Negotiated Procurement - Emergency Cases
Failed under Section 41 (c) |  |  |  | Negotiated Procurement - Take-Over of Contracts
Contract was extended |  |  |  | Negotiated Procurement - Adjacent or Contiguous
Contract was renewed |  |  |  | Negotiated Procurement - Agency-to-Agency
Cancelled |  |  |  | Negotiated Procurement - Scientific, Scholarly, Artistic Work, Exclusive Technology and Media Services
Others, please encode directly on the cell |  |  |  | Negotiated Procurement - Highly Technical Consultants
Negotiated Procurement - Defense Cooperation Agreement
Negotiated Procurement - Small Value Procurement
Negotiated Procurement - Lease of Real Property and Venue
Negotiated Procurement - NGO Participation
Negotiated Procurement - Community Participation
Negotiated Procurement - UN Agencies, Int'l Organizations or International Financing Institutions
Negotiated Procurement - Direct Retail Purchase of Petroleum Fuel, Oil and Lubricant Products, Electronic Charging Devices, and Online Subscriptions
Foreign Guidelines - Competitive Bidding
Foreign Guidelines - Alternative Method
Competitive Dialogue
Unsolicited Offer with Bid Matching
Direct Acquisition
Direct Sales
Direct Procurement for Science, Technology, and Innovation
Others, specify in the remarks: Mode of Procurement use <Mode>